## 395-550
ETNT Article-focused template:
https://docs.google.com/a/galvanized.com/document/d/1QOjKruOSN_9ADKvfl7eKSEyVikarBIQLfEV5FMkK8Qk/edit
ETNT Main-story focused template:
https://docs.google.com/a/galvanized.com/document/d/1fZy39nrUd_4qbecB1hbckphDuonQLNhmBXoH2A81J6s/edit
Promo template:
https://docs.google.com/document/d/1ACfRvnZX1CBly-w_TvvWi2roq97Fbw_o8wMzfx8ut6c/edit
DE preview (new issue)
https://docs.google.com/document/d/1-puBVxbgIcazCEv53y3uOwDdBg5ViDgF8YYktJSQhZE/edit
NOTES
No. | List | Pickup? | Due | Releases | Day | Design | Content | Promo | Who | Status/ Comments
386 | ETNT |  | Fri | 2016-01-11 | Mon | Article | kindbarrank | teaspot | DM
387 | ETNT |  | Mon | 2016-01-12 | Tue | Article | traderjoes | greentea | DM | green tea now in paperback
388 | ETNT |  | Fri | 2016-01-12 | Tue |  | greenteapaperonsale |  | JP
389 | ETNT |  | Tues | 2016-01-13 | Wed | Main Story | cheapfoodsforabs | zbapp | DM
390 | ETNT |  | Weds | 2016-01-14 | Thu | Article | foodshungrier | etntde | DM
391 | ETNT |  | Thurs | 2016-01-15 | Fri | Article | suguariestmeals | etntabs | DM
392 | ETNT |  | Thurs | 2016-01-16 | Sat | Article | sodabellyvideo | teacleanse | DM
393 | ETNT |  | Fri | 2016-01-17 | Sun |  | etntdefulllist |  | JP
394 | ETNT |  | Fri | 2016-01-18 | Mon | Article | turkeyneck | etntgame | DM
395 | ETNT |  | Fri | 2016-01-19 | Tue | Article | worstbedtimefoods | zbsmoothies | DM
396 | ZB | Y | Tue | 2016-01-19 | Tue | ZBD Main Story |  | n/a | DC | Pick up 385
397 | ZB |  | Tue | 2016-01-19 | Tue | Promo | smoothiesonsale | n/a | JP | Throttled over 1 day
398 | ETNT |  | Tue | 2016-01-20 | Wed | Main Story | metabolismbreakfast | greentea | DM
399 | ETNT |  | Wed | 2016-01-21 | Thu | Article | melissamccarthy | zbapp | DM
400 | ETNT |  | Thu | 2016-01-22 | Fri | Article | metabolismmyths | zbcook | DM
401 | ETNT |  | Thu | 2016-01-23 | Sat | Article | bulkguide | etntabs | DM
402 | ETNT |  | Thu | 2016-01-24 | Sun | Promo TBD | hamptonslane | n/a | JP
403 | ETNT |  | Fri | 2016-01-25 | Mon | Article | bananasandyourbody | zbsmoothies | DM
404 | ZBD |  | Thu | 2016-01-25 | Mon | ZBD Main Story |  | n/a | JP | STARTS WEEKLY PRODUCTION
405 | ETNT |  | Mon | 2016-01-26 | Tue | Main Story | walkingtips | etntde | DM
406 | ETNT |  | Tue | 2016-01-27 | Wed | Article | fullsodaranking | zerobelly.com | DM
407 | ETNT |  | Tue | 2016-01-27 | Wed | Promo | absebookfemale |  | JP
408 | ETNT |  | Wed | 2016-01-28 | Thu | Article | lazyways | teacleanse | DM
409 | ETNT |  | Thu | 2016-01-29 | Fri | Article | mcdonaldsbreakfast | etntgame | DM
410 | ETNT |  | Thu | 2016-01-30 | Sat | Article | cheapstorealdis | greentea | DM
411 | ETNT |  | Thu | 2016-01-31 | Sun | Promo TBD | zbappnewimp | n/a | JP
412 | ETNT |  | Fri | 2016-02-01 | Mon | Main Story | anistonbreakfast | zbapp | DM
413 | ZBD |  | Wed | 2016-02-01 | Mon | ZBD Main Story | 7bestcombos | n/a | JP
414 | ETNT |  | Mon | 2016-02-02 | Mon | Article | etntsurvey | n/a | DM
415 | ETNT |  | Mon | 2016-02-02 | Tue | Article | coconutoil | etntabs | DM
416 | ETNT |  | Tue | 2016-02-03 | Wed | Article | pastaranking | zbsmoothies | DM
417 | ETNT |  | Wed | 2016-02-04 | Thu | Article | sixpackhabits | teacleanse | DM
418 | ETNT |  | Thu | 2016-02-05 | Fri | Article | carbcheattrick | zbapp | DM
419 | ETNT |  | Thu | 2016-02-06 | Sat | Main Story | potatochipranking | zbcook | DM
420 | ETNT |  | Thu | 2016-02-07 | Sun | Promo TBD | teacleanseww | n/a | JP
421 | ZBD |  | Fri | 2016-02-08 | Mon | Article | etntagingguide | greentea | DM
422 | ETNT |  | Wed | 2016-02-08 | Mon | ZBD Main Story | 25nevereat | n/a | JP
423 | ETNT |  | Mon | 2016-02-09 | Tue | Article | dietplanquiz | etntgame | DM
424 | ETNT |  | Tue | 2016-02-10 | Wed | Article | eatinghabits | teaspot | DM
425 | ETNT |  | Wed | 2016-02-11 | Thu | Article | drinkingrules | etntabs | DM
426 | ETNT |  | Thu | 2016-02-12 | Fri | Main Story | olivegardenranking | teacleanse | DM
427 | ETNT |  | Thu | 2016-02-13 | Sat | Article | valentinesday | etntde | DM
428 | ETNT |  | Thu | 2016-02-14 | Sun | Promo TBD | zbsmoothies2 | n/a | JP
429 | ZBD |  | Thu | 2016-02-15 | Mon | Article | peanutbutterhealth | zbapp | DM | Did not send
430 | ETNT |  | Wed | 2016-02-15 | Mon | ZBD Main Story | 30reasons | n/a | JP
431 | ETNT |  | Thu | 2016-02-16 | Tue | Article | unhealthiestfoods | zbsmoothies | DM | President's Day, schedule adjusted
432 | ETNT |  | Tue | 2016-02-17 | Wed | Article | peanutbutterhealth | zbapp | DM | Sending out Monday's missed newsletter
433 | ETNT |  | Wed | 2016-02-18 | Thu | Main Story | costcosecrets | zbd | DM
434 | ETNT |  | Thu | 2016-02-19 | Fri | Article | fishranking | etntabs | DM
435 | ETNT |  | Thu | 2016-02-20 | Sat | Article | alyssamilano | etntde | DM
436 | ETNT |  | Thu | 2016-02-21 | Sun | Promo TBD | etntde | n/a | JP
437 | ZBD |  | Fri | 2016-02-22 | Mon | Article | worstfastfooddishes | teacleanse | DM
438 | ETNT |  | Wed | 2016-02-22 | Mon | ZBD Main Story | bestcarbs20 | n/a | JP
439 | ETNT |  | Mon | 2016-02-23 | Tue | Article | Proteinsnacks | zbsmoothies | DM
440 | ETNT |  | Tue | 2016-02-24 | Wed | Main Story | beatweightlossplateau | etntgame | DM
441 | ETNT |  | Wed | 2016-02-25 | Thu | Article | badhealthyfoods | zbapp | DM
442 | ETNT |  | Thu | 2016-02-26 | Fri | Article | burgerranking | greentea | DM | please use cup of matcha image for promo
443 | ETNT |  | Thu | 2016-02-27 | Sat | Article | mcdonaldsfacts | etntabs | DM
444 | ETNT |  | Thu | 2016-02-28 | Sun | Promo TBD | backlist | n/a | JP
445 | ZBD |  | Fri | 2016-02-29 | Mon | Article | expertsprocessedfoods | etntde | DM
446 | ETNT |  | Wed | 2016-02-29 | Mon | ZBD Main Story | worstabs25 | n/a | JP
447 | ETNT |  | Mon | 2016-03-01 | Tue | Main Story | supermarketswaps | teacleanse | DM
448 | ETNT |  | Tue | 2016-03-02 | Wed | Article | applecidervinegar | zerobelly.com | DM
449 | ETNT |  | Wed | 2016-03-03 | Thu | Article | worstfiberfoods | 2015book | DM
450 | ETNT |  | Thu | 2016-03-04 | Fri | Article | secretmenuitems | zbapp | DM
451 | ETNT |  | Thu | 2016-03-05 | Sat | Article | weightlossquestionsdrink | zbsmoothies | DM
452 | ETNT |  | Thu | 2016-03-06 | Sun | Promo TBD | teacleanseww | n/a | JP
453 | ZBD |  | Fri | 2016-03-07 | Mon | Main Story | metabolismmistakes | etntabs | DM
454 | ETNT |  | Wed | 2016-03-07 | Mon | ZBD Main Story | bestsmoothies8 | n/a | JP
455 | ETNT |  | Mon | 2016-03-08 | Tue | Article | sleepdiet | etntde | DM
456 | ETNT |  | Tue | 2016-03-09 | Wed | Article | restaurantsalads | teaspot | DM
457 | ETNT |  | Wed | 2016-03-10 | Thu | Article | lowcarbfruitsveggies | zbcook | DM
458 | ETNT |  | Thu | 2016-03-11 | Fri | Article | worsthealthysnacks | ctnteasy | DM
459 | ETNT |  | Tue | 2016-03-11 | Fri | Promo | greenteapaperonly | n/a | JP
460 | ETNT |  | Thu | 2016-03-12 | Sat | Main Story | chipotleranked | zbapp | DM
461 | ETNT |  | Thu | 2016-03-13 | Sun | Promo TBD | zbappnewimp | n/a | JP
462 | ZBD |  | Fri | 2016-03-14 | Mon | Article | stretchmarks | greentea | DM
463 | ETNT |  | Wed | 2016-03-14 | Mon | ZBD Main Story | besttips50 | n/a | JP
464 | ETNT |  | Mon | 2016-03-15 | Tue | Article | worsttacos | zbsmoothies | DM
465 | ETNT |  | Tue | 2016-03-16 | Wed | Article | snackguide | etntexpecting | DM
466 | ZBD |  | Tue | 2016-03-16 | Wed | Promo TBD | zbsmoothiesgma | n/a | JP
467 | ETNT |  | Wed | 2016-03-17 | Thu | Article | successfulpeoplefoods | etntabs | DM | Promo may need to be a split test.
468 | ETNT |  | Thu | 2016-03-18 | Fri | Main Story | heatlhiestfats | teacleanse | DM
469 | ETNT |  | Thu | 2016-03-19 | Sat | Article | healthyboozebenefits | ctnteasy | DM
470 | ETNT |  | Thu | 2016-03-20 | Sun | Promo TBD | etntabs | n/a | JP
471 | ZBD |  | Fri | 2016-03-21 | Mon | Article | littlethingsmakingyoufat | zbapp | DM
472 | ETNT |  | Wed | 2016-03-21 | Mon | ZBD Main Story |  | n/a | JP
473 | ETNT |  | Mon | 2016-03-22 | Tue | Article | bestspringfoods | zbsmoothies | DM
474 | ETNT |  | Tue | 2016-03-23 | Wed | Article | weightlossinfluencers | zbcook | DM
475 | ETNT |  | Wed | 2016-03-24 | Thu | Main Story | proteinpowders | greentea | DM
476 | ETNT |  | Wed | 2016-03-25 | Fri | Article | kendalljennereats | etntabs | DM | Moved up schedulewise
477 | ETNT |  | Thu | 2016-03-26 | Sat | Article | aldismoneytips | teacleanse | DM
478 | ETNT |  | Wed | 2016-03-27 | Sun | Promo TBD | ctnteasy | n/a | JP | Moved up schedulewise
479 | ZBD |  | Thu | 2016-03-28 | Mon | Article | overeatingandfat | ctnteasy | DM | Moved up schedulewise
480 | ETNT |  | Tue | 2016-03-28 | Mon | ZBD Main Story | dinners4 | n/a | JP | Moved up schedulewise
481 | ETNT |  | Mon | 2016-03-29 | Tue | Article | walmartswaps | zbsmoothies | DM
482 | ETNT |  |  | 2016-03-29 | Tue | Promo TBD | etntdespring | n/a | JP
483 | ETNT |  | Tue | 2016-03-30 | Wed | Main Story | nutritionistfastfood | etntde | DM
484 | ETNT |  | Wed | 2016-03-31 | Thu | Article | bikinibodyfoods | ctntskinny | DM
485 | ETNT |  | Thu | 2016-04-01 | Fri | Article | bestworstcelebs | greentea | DM
486 | ETNT |  | Thu | 2016-04-02 | Sat | Article | bestnutritionbars | etntabs | DM
487 | ETNT |  | Thu | 2016-04-03 | Sun | Promo TBD | teacleanseww3 | n/a | JP
488 | ZBD |  | Fri | 2016-04-04 | Mon | Article | petpeeves | zbcook | DM
489 | ETNT |  | Wed | 2016-04-04 | Mon | ZBD Main Story | proteins20 | n/a | JP
490 | ETNT |  | Mon | 2016-04-05 | Tue | Main Story | hottestrestaurants | AARP | DM
491 | ETNT |  |  | 2016-04-05 | Tue | Promo TBD | AARP | zbapp | JP
492 | ETNT |  | Tue | 2016-04-06 | Wed | Article | frozencleaneats | ctnteasy | DM
493 | ETNT |  | Wed | 2016-04-07 | Thu | Article | worstbreakfasthabits | teacleanse | DM
494 | ETNT |  | Thu | 2016-04-08 | Fri | Article | paneraranking | Lipton | DM
495 | ETNT |  | Thu | 2016-04-09 | Sat | Article | carbloversguide | greentea | DM
496 | ETNT |  | Thu | 2016-04-10 | Sun | Promo TBD | zbapp | n/a | JP
497 | ZBD |  | Fri | 2016-04-11 | Mon | Main Story | alwayshungry | slimfast | DM
498 | ETNT |  | Wed | 2016-04-11 | Mon | ZBD Main Story |  | n/a | JP
499 | ETNT |  | Mon | 2016-04-12 | Tue | Article | vitaminbellybloat | etntabs | DM
500 | ETNT |  | Mon | 2016-04-13 | Wed | Article | whyyougainedweight | AARP | DM
501 | ETNT |  | Tue | 2016-04-14 | Thu | Article | proteinpowdertricks | ctnteasy | DM | Moved up in the schedule
502 | ETNT |  | Tue | 2016-04-15 | Fri | Article | badfoodsnowgood | teacleanse | DM | Moved up in the schedule
503 | ETNT |  | Wed | 2016-04-16 | Sat | Main Story | chickfilaranking | zbd | DM | Moved up in the schedule
504 | ETNT |  | Wed | 2016-04-17 | Sun | Promo TBD | etntabs | n/a | JP | Moved up in the schedule
505 | ZBD |  | Wed | 2016-04-18 | Mon | Article | bestfatburningfoods | teaspot | DM | Moved up in the schedule
506 | ETNT |  | Tue | 2016-04-18 | Mon | ZBD Main Story | omega3 | n/a | JP | Moved up in the schedule
507 | ETNT |  | Mon | 2016-04-19 | Tue | Article | worstbreakfast | Lipton | DM
508 | ETNT |  | Mon | 2016-04-20 | Wed | Promo TBD | magcoversurvey | n/a | JP | John added-drive to ETNT Mag cover survey
509 | ETNT |  | Tue | 2016-04-20 | Wed | Article | proteinhabit | etntde | DM | Custom button a/b test
510 | ETNT |  | Wed | 2016-04-21 | Thu | Article | targetmoneytips | AARP | DM
511 | ETNT |  | Thu | 2016-04-22 | Fri | Main Story | peanutbutterrank | zbcook | DM | Custom Button a/b test - part 2
512 | ETNT |  | Thu | 2016-04-23 | Sat | Article | starbucksbreakfast | slimfast | DM | http://www.eatthis.com/slimfast-recipes
513 | ETNT |  | Thu | 2016-04-24 | Sun | Promo TBD | zbsmoothies | n/a | JP
514 | ZBD |  | Fri | 2016-04-25 | Mon | Article | latenighthabits | zbapp | DM
515 | ETNT |  | Wed | 2016-04-25 | Mon | ZBD Main Story | wakeup14 | n/a | JP
516 | ETNT |  | Mon | 2016-04-26 | Tue | Article | breadbrands | Lipton | DM
517 | ETNT |  | Tue | 2016-04-27 | Wed | Article | fiveguys | greentea | DM
518 | ETNT |  | Wed | 2016-04-28 | Thu | Main Story | slowcooker | naughtydiet | DM
519 | ETNT |  | Thu | 2016-04-29 | Fri | Article | cellulite | AARP | DM | Also: multiple subject line test with a "batch" subject line
520 | ETNT |  | Thu | 2016-04-30 | Sat | Article | mcdonaldsranking | etntde | DM
521 | ETNT |  | Thu | 2016-05-01 | Sun | Promo TBD | naughtydiet | n/a | JP
522 | ZBD |  | Fri | 2016-05-02 | Mon | Article | guthealth | ctnteasy | DM
523 | ETNT |  | Wed | 2016-05-02 | Mon | ZBD Main Story |  | n/a | JP | CANCELED
524 | ETNT |  | Mon | 2016-05-03 | Tue | Article | brazilianguide | zbapp | DM
525 | ETNT |  | Fri | 2016-05-03 | Tue | Promo TBD | aarp | n/a | JP | Extra promo to sync with AARP push to their list
526 | ETNT |  | Tue | 2016-05-04 | Wed | Main Story | worstweightloss | entnabs | DM
527 | ETNT |  | Wed | 2016-05-05 | Thu | Article | untrustworthyfoods | zbcook | DM
528 | ETNT |  | Thu | 2016-05-06 | Fri | Article |  | greentea | DM
529 | ETNT |  | Thu | 2016-05-07 | Sat | Article |  | etntsurvey | DM | John changed promo 5/5
530 | ETNT |  | Thu | 2016-05-08 | Sun | Promo TBD | expecting | n/a | JP | John changed promo 5/5
531 | ZBD |  | Fri | 2016-05-09 | Mon | Article |  | zbd | DM
532 | ETNT |  | Wed | 2016-05-09 | Mon | ZBD Main Story | newweapon | n/a | JP
533 | ETNT |  | Mon | 2016-05-10 | Tue | Main Story |  | zbsmoothies | DM
534 | ZB |  | Mon | 2016-05-09 | Mon | Survey | subsurvey | n/a | JP
535 | ETNT |  | Tue | 2016-05-11 | Wed | Article |  | etntexpecting | DM
536 | ETNT |  | Wed | 2016-05-12 | Thu | Article |  | naughtydiet | DM
537 | ETNT |  | Thu | 2016-05-13 | Fri | Article |  | etntexpecting | DM
538 | ETNT |  | Thu | 2016-05-14 | Sat | Article |  | AARP | DM
539 | ETNT |  | Thu | 2016-05-15 | Sun | Promo TBD | teacleanse | n/a | JP
540 | ZBD |  | Fri | 2016-05-16 | Mon | Main Story |  | teacleanse | DM
541 | ETNT |  | Wed | 2016-05-16 | Mon | ZBD Main Story |  | n/a | JP
542 | ETNT |  | Mon | 2016-05-17 | Tue | Article |  | etntexpecting | DM | book on-sale date
543 | ETNT |  | Tue | 2016-05-18 | Wed | Article |  | zbapp | DM
544 | ETNT |  | Mon | 2016-05-18 | Wed | Promo TBD | etntexpecting |  | JP | DZ on GMA Promoting book
545 | ETNT |  | Wed | 2016-05-19 | Thu | Article |  | teaspot | DM
546 | ETNT |  | Thu | 2016-05-20 | Fri | Article |  |  | DM
547 | ETNT |  | Thu | 2016-05-21 | Sat | Main Story |  |  | DM
548 | ETNT |  | Thu | 2016-05-22 | Sun | Promo TBD |  | n/a | JP
549 | ZBD |  | Fri | 2016-05-23 | Mon | Article |  |  | DM
550 | ETNT |  | Wed | 2016-05-23 | Mon | ZBD Main Story |  | n/a | JP
551 | ETNT |  | Mon | 2016-05-24 | Tue | Article |  |  | DM
552 | ETNT |  | Tue | 2016-05-25 | Wed | Article |  |  | DM
553 | ETNT |  | Wed | 2016-05-26 | Thu | Article |  |  | DM
554 | ETNT |  | Thu | 2016-05-27 | Fri | Main Story |  |  | DM
555 | ETNT |  | Thu | 2016-05-28 | Sat | Article |  |  | DM
556 | ETNT |  | Thu | 2016-05-29 | Sun | Promo TBD |  | n/a | JP
557 | ZBD |  | Fri | 2016-05-30 | Mon | Article |  |  | DM
558 | ETNT |  | Wed | 2016-05-30 | Mon | ZBD Main Story |  | n/a | JP
559 | ETNT |  | Mon | 2016-05-31 | Tue | Article |  |  | DM
560 | ETNT |  | Tue | 2016-06-01 | Wed | Article |  |  | DM
561 | ETNT |  | Wed | 2016-06-02 | Thu | Main Story |  |  | DM
562 | ETNT |  | Thu | 2016-06-03 | Fri | Article |  |  | DM
563 | ETNT |  | Thu | 2016-06-04 | Sat | Article |  |  | DM
564 | ETNT |  | Thu | 2016-06-05 | Sun | Promo TBD |  | n/a | JP
565 | ZBD |  | Fri | 2016-06-06 | Mon | Article |  |  | DM
566 | ETNT |  | Wed | 2016-06-06 | Mon | ZBD Main Story |  | n/a | JP
567 | ETNT |  | Mon | 2016-06-07 | Tue | Article |  |  | DM
568 | ETNT |  | Tue | 2016-06-08 | Wed | Main Story |  |  | DM
569 | ETNT |  | Wed | 2016-06-09 | Thu | Article |  |  | DM
570 | ETNT |  | Thu | 2016-06-10 | Fri | Article |  |  | DM
571 | ETNT |  | Thu | 2016-06-11 | Sat | Article |  |  | DM
572 | ETNT |  | Thu | 2016-06-12 | Sun | Promo TBD |  | n/a | JP
573 | ZBD |  | Fri | 2016-06-13 | Mon | Article |  |  | DM
574 |  |  | Wed | 2016-06-13 | Mon | ZBD Main Story |  | n/a | JP

## archive 245-395
http://www.eatthis.com/your-day-in-health-031416
https://docs.google.com/a/galvanized.com/document/d/1QOjKruOSN_9ADKvfl7eKSEyVikarBIQLfEV5FMkK8Qk/edit
ETNT Main-story focused template:
https://docs.google.com/a/galvanized.com/document/d/1fZy39nrUd_4qbecB1hbckphDuonQLNhmBXoH2A81J6s/edit
Promo template:
https://docs.google.com/document/d/1ACfRvnZX1CBly-w_TvvWi2roq97Fbw_o8wMzfx8ut6c/edit
DE preview (new issue)
https://docs.google.com/document/d/1-puBVxbgIcazCEv53y3uOwDdBg5ViDgF8YYktJSQhZE/edit
NOTES
No. | Brand | Pickup? | Due | Releases | Day | Content | Design | Promo | Who | Status/ Comments
246 | ETNT |  | 2015-09-15 14:00 | 2015-09-16 | Weds | rapidlossdrinks | Article | etntde | MF
247 | ETNT |  | 2015-09-16 14:00 | 2015-09-17 | Thurs | fastfoodondrugs | Article | zerobelly.com | MF
248 | ETNT |  | 2015-09-17 14:00 | 2015-09-18 | Fri | turnoffhormones | Main Story | zbd | MF
249 | ETNT |  | 2015-09-17 14:00 | 2015-09-20 | Sat/Sun | bestnutritiontips | Article | none | MF
250 | ETNT |  | 2015-09-18 12:00 | 2015-09-21 | Mon | giveupdairy | Article | zbapp | MF
252 | ETNT |  |  | 2015-09-19 | Sat | zbapetnt | ETNTPromo1 |  | JP
253 | ZBD |  |  | 2015-09-20 | Sun | zbapzbd | ZBDPromo1 |  | JP
254 | ZBD |  | Mon | 2015-09-20 | Mon | sevendaycleanse | ZBD Main Story |  | JP
251 | ETNT |  | Mon | 2015-09-22 | Tues | highproteinfoods | Article | teacleanse | MF
255 | ETNT |  | Tues | 2015-09-23 | Weds | obesestate | Article | zbcook | MF
256 | ETNT |  | Weds | 2015-09-24 | Thurs | nutritionmyths | Main Story | 2015book | MF
257 | ETNT |  | Thurs | 2015-09-25 | Fri | fullfat | Article | zbapp | MF
258 | ETNT |  | Weds | 2015-09-26 | Sat | cookbookpromo1etnt |  |  | JP
259 | ZBD |  | Weds | 2015-09-26 | Sat | cookbookpromo1zbd |  |  | JP
260 | ——
261 | ETNT |  | Thurs | 2015-09-27 | Sun | badhabits | Article | etntde | MF
262 | ZBD | Y | Thurs | 2015-09-28 | Mon |  | ZBD Main Story |  | DC
263 | ETNT |  | Fri | 2015-09-28 | Mon | kickfridge | Article | none | MF
264 | ETNT |  | Mon | 2015-09-29 | Tues | skinnypeople | Article | teacleanse | MF
265 | ETNT |  | Tues | 2015-09-30 | Weds | cheapabs | Main Story |  | MF
266 | ETNT |  | Weds | 2015-10-01 | Thurs | weightsleep | Article | zbapp | MF
267 | ETNT |  | Thurs | 2015-10-02 | Fri | carbsabs | Article | zbd | MF
268 | ETNT
269 | ETNT | Y |  | 2015-10-03 | Sat | zbapetnt |  |  | DC | sample test- resend
270 | ETNT |  | Thurs | 2015-10-04 | Sun | unhealthiest | Article | teacleanse | MF
271 | ZBD |  | Thurs | 2015-10-05 | Mon | sixspices | ZBD Main Story |  | JP
272 | ETNT |  | Fri | 2015-10-05 | Mon | grocerylist | Article | zbcook | MF
273 | ETNT |  | Mon | 2015-10-06 | Tues | grocerystoreripoffs | Article | none | MF | *Knock-knock winback 1 sent here
274 | ETNT |  | Tues | 2015-10-07 | Weds | mcdonalds | Main Story | greentea | MF
275 | ETNT |  | Weds | 2015-10-08 | Thurs | bananas | Article | zerobelly.com | MF | zb.com: 7 Ways to Get Abs
276 | ETNT |  | Thurs | 2015-10-09 | Fri | portions | Article | teacleanse | MF
277 |  | Y |  | 2015-10-10 | Sat | zbapetnt |  |  | DC | to DE preview list
278 |  | Y |  | 2015-10-10 | Sat | zbapetnt |  |  | DC | remainder of test- resend
279 | ETNT |  | Thurs | 2015-10-11 | Sun | bestteas | Article | zbapp | MF
280 | ZBD | Y | Thurs | 2015-10-12 | Mon |  | ZBD Main Story |  | DC
281 | ETNT |  | Fri | 2015-10-12 | Mon |  | Main Story | eatthis.com | MF
282 | ETNT |  | Mon | 2015-10-13 | Tues | frenchfry | Article | teacleanse | MF
283 | ETNT |  | Tues | 2015-10-14 | Weds | dominos | Article | greentea | MF
284 | ETNT |  | Weds | 2015-10-15 | Thurs | proteinsideeffects | Article | none | DM
285 | ETNT |  | Thurs | 2015-10-16 | Fri | worstbreakfast | Article | zbd | DM
286 | ETNT |  | Thurs | 2015-10-18 | Sun | hairloss | Main Story | zbapp | DM
287 | ETNT |  |  | 2015-10-17 | Sat | gtdpromo1etnt |  |  | JP
288 | ZBD |  | Thurs | 2015-10-19 | Mon |  | ZBD Main Story |  | JP
289 | ETNT |  | Fri | 2015-10-19 | Mon | biggestloser | Article | etntde | DM
290 | ETNT |  | Mon | 2015-10-20 | Tues | sodasranked | Article | zbcook | DM
291 | ETNT |  | Tues | 2015-10-21 | Weds | meltfatwithtea | Article | eatthis.com | DM
292 | ETNT |  | Weds | 2015-10-22 | Thurs | bestsoups | Article | none | DM
293 | ETNT |  | Thurs | 2015-10-23 | Fri | chinesefood | Main Story | greentea | DM
294 | ETNT |  | Thurs | 2015-10-24 | Sat | worstfood | Article | teacleanse | DM | Pub date for print version of teacleanse.
295 | ETNT |  |  | 2015-10-25 | Sun | tcpaper |  |  | JP | Tea cleanse now in paperback
296 | ZBD |  | Thurs | 2015-10-26 | Mon |  | ZBD Main Story |  | DC
297 | ETNT |  | Fri | 2015-10-26 | Mon | lose4inches | Article | 2015book | DM
298 | ETNT |  | Mon | 2015-10-27 | Tues | worstprotein | Article | zerobelly.com | DM
299 | ETNT |  | Tues | 2015-10-28 | Weds | hallowencandy | Article | zbapp | DM
300 | ETNT |  | Weds | 2015-10-29 | Thurs | dietsodarank | Main Story | greentea | DM
301 | ETNT |  | Thurs | 2015-10-30 | Fri | cancercausingfoods | Article | teaspot | DM | Launch date for this partnership
302 | ETNT |  | Thurs | 2015-10-31 | Sat | supplement | Article | zbcook | DM
304 | ZBD | Y | Thurs | 2015-11-02 | Mon |  | ZBD Main Story |  | JP
305 | ETNT |  | Fri | 2015-11-02 | Mon | metabolismhabits | Article | etntde | DM
306 | ETNT |  | Mon | 2015-11-03 | Tues | worstpackagedfoods | Article | none | DM
307 | ETNT |  | Tues | 2015-11-04 | Weds | fatburningsoups | Main Story | teacleanse | DM
308 | ETNT |  | Weds | 2015-11-05 | Thurs | adele | Article | zbapp | DM
309 | ETNT |  | Weds | 2015-11-05 | Thurs | de4mid | DEPreview |  | JP | Push to digital edition audience only
310 | ETNT |  | Thurs | 2015-11-06 | Fri | fastfoodantibiotics | Article | greentea | DM
311 | ETNT |  | Thurs | 2015-11-07 | Sat | fastfoodbreakfast | Article | teaspot | DM
312 | ZBD |  | Thurs | 2015-11-09 | Mon |  | ZBD Main Story |  | DC
313 | ETNT |  | Fri | 2015-11-09 | Mon | giveupalcohol | Article | etntde | DM
314 | ETNT |  | Mon | 2015-11-10 | Tues | bananashealth | Main Story | zbd | DM
315 | ETNT |  | Tues | 2015-11-11 | Weds | bedtimehabits | Article | zbapp | DM
316 | ETNT |  | Weds | 2015-11-12 | Thurs | celebrityweightloss | Article | teacleanse | DM
317 | ETNT |  | Thurs | 2015-11-13 | Fri | worstcarbs | Article | zbcook | DM
318 | ETNT |  | Thurs | 2015-11-14 | Sat | energydrinks | Article | none | DM
319 | ETNT |  | Thurs | 2015-11-15 | Sun | zbapzbd2 | ETNTPromo1 |  | JP
320 | ZBD | Y | Thurs | 2015-11-16 | Mon |  | ZBD Main Story |  | JP
321 | ETNT |  | Fri | 2015-11-16 | Mon | fightbellyfat | Main Story | teaspot | DM
322 | ETNT |  | Mon | 2015-11-17 | Tues | proteinmetabolism | Article | bulu | DM
323 | ETNT |  | Tues | 2015-11-18 | Weds | bestyogurts | Article | greentea | DM
324 | ETNT |  | Weds | 2015-11-19 | Thurs | nighttimecarbtrick | Article | etntde | DM
325 | ETNT |  | Thurs | 2015-11-20 | Fri | horrificfoods | Article | zbd | DM
326 | ETNT |  | Thurs | 2015-11-21 | Sat | foodsexpertswonttouch | Main Story | zbapp | DM
327 | ETNT |  | Thurs | 2015-11-21 | Sun | TeaspotPromo
328 | ZBD |  | Thurs | 2015-11-23 | Mon |  | ZBD Main Story |  | DC
329 | ETNT |  | Fri | 2015-11-23 | Mon | foodcombos | Article | etntde | DM
330 | ETNT |  | Mon | 2015-11-24 | Tue | losefiveinchesoffat | Article | teacleanse | DM
331 | ETNT |  | Tues | 2015-11-25 | Wed | peanutbutter | Article | teaspot | DM
332 | ETNT |  | Weds | 2015-11-26 | Thu | bananatruth | Article | zbcook | DM
333 | ETNT |  | Thurs | 2015-11-27 | Fri | worstcereals | Main Story | bulu | DM
334 | ETNT |  | Thurs | 2015-11-28 | Sat | fattyfoodsoneinch | Article | zbd | DM
335 | ETNT | Y | Weds | 11/29/2015 | Sun | tcpaper |  |  | JP | Tea cleanse now in paperback. Pick up project No. 295
336 | ZBD |  | Thurs | 2015-11-30 | Mon | personaltrain | ZBD Main Story |  | JP
337 | ETNT |  | Fri | 2015-11-30 | Mon | fiftysnacks | Article | eatthis.com | DM
338 | ETNT |  | Mon | 2015-12-01 | Tue | destructivefoods | Article | zbapp | DM
339 | ETNT |  | Tues | 2015-12-02 | Wed | bestdrinks | Article | teaspot | DM
340 | ETNT |  | Weds | 2015-12-03 | Thu | salmontruth | Main Story | greentea | DM
341 | ETNT |  | Thurs | 2015-12-04 | Fri | paleofoods | Article | zbcook | DM
342 | ETNT |  | Thurs | 2015-12-05 | Sat | yourbodyoneggs | Article | bulu | DM
343 | ETNT |  | Thurs | 2015-12-06 | Sun | ZBTrade | ZBDPromo1 |  | JP
344 | ETNT | Y | Thurs | 2015-12-07 | Mon |  | ZBD Main Story |  | DC
345 | ETNT |  | Fri | 2015-12-07 | Mon | proteineverygoal | Article | teacleanse | DM
346 | ETNT |  | Mon | 2015-12-08 | Tue | worstfoods30 | Article | zbapp | DM
347 | ETNT |  | Tues | 2015-12-09 | Wed | cheapwaysloseweight | Main Story | etntgame | DM | NL_ETNT_Game_Logo.jpg
348 | ETNT |  | Weds | 2015-12-10 | Thu | badhabitssickandfat | Article | teaspot | DM
349 | ETNT |  | Thurs | 2015-12-11 | Fri | coffeeandyourbody | Article | greentea | DM
350 | ETNT |  | Thurs | 2015-12-12 | Sat | TeaspotPromoGift |  |  | JP
351 | ETNT |  | Thurs | 2015-12-12 | Sat | worstmcdonaldsitem | Article | bulu | DM
352 | ETNT |  | Thurs | 2015-12-14 | Mon |  | ZBD Main Story |  | JP
353 | ETNT |  | Fri | 2015-12-14 | Mon | coffeesecret | Article | eatthis.com | DM
354 | ETNT |  | Mon | 2015-12-15 | Tue | peanutbutterranking | Main Story | etntgame | DM
355 | ETNT |  | Tues | 2015-12-16 | Wed | worstcarbhabit | Article | teacleanse | DM
356 | ETNT |  | Weds | 2015-12-17 | Thu | bedtimedrink | Article | zbapp | DM
357 | ETNT |  | Thurs | 2015-12-18 | Fri | worstbreakfast | Article | teaspot | DM
358 | ETNT |  | Thurs | 2015-12-19 | Sat | etntworstchain | Article | zbcook | DM
359 | ETNT |  | Fri | 2015-12-20 | Sun | etntgame | Custom |  | JP
360 | ETNT | Y | Thurs | 2015-12-21 | Mon |  | ZBD Main Story |  | DC
361 | ETNT |  | Fri | 2015-12-21 | Mon | hairloss | Main Story | etntabs | DM
362 | ETNT |  | Mon | 2015-12-22 | Tue | worstcarbhabits | Article | greentea | DM
363 | ETNT |  | Mon | 2015-12-23 | Wed | de5preview | DEPreview |  | JP | Pushed back a day to match issue live date
364 | ETNT |  | Tues | 2015-12-23 | Wed | proteinmistake | Article | etntde | DM
365 | ETNT |  | Weds | 2015-12-24 | Thu | mcdonaldsmenucut | Article | 2015book | DM
366 | ETNT |  | Weds | 2015-12-25 | Fri | worstwaystoeatbananas | Article | zbcook | DM
367 | ETNT |  | Thurs | 2015-12-26 | Sat | worstflatbellymistake | Main Story | teacleanse | DM
368 | ETNT |  | Thurs | 2015-12-27 | Sun | greenteapaperpre | TBD |  | JP
369 | ZBD |  | Thurs | 2015-12-28 | Mon | successfirefighter | ZBD Main Story |  | JP
370 | ETNT |  | Thurs | 2015-12-28 | Mon | kardashian | Article | etntgame | DM
371 | ETNT |  | Mon | 2015-12-29 | Tue | foodsthatageyou | Article | eatthis.com | DM
372 | ETNT |  | Tues | 2015-12-30 | Wed | loseweightatdinner | Article | zbapp | DM
373 | ETNT |  | Weds | 2015-12-31 | Thu | bestsupplement | Article | zbd | DM
374 | ETNT |  | Weds | 2016-01-01 | Fri | dietexpertresolutions | Article | greentea | DM
375 | ETNT |  | Thurs | 2016-01-02 | Sat | worstbellymistake | Main Story | etntabs | DM
376 | ETNT |  | Thurs | 2016-01-03 | Sun | etntabsonsale | TBD |  | JP
377 | ZBD | Y | Thurs | 2016-01-04 | Mon |  | ZBD Main Story |  | DC
378 | ETNT |  | Thurs | 2016-01-04 | Mon | Weightlossqs | Article | teacleanse | DM
379 | ETNT |  | Mon | 2016-01-05 | Tue | cleaneating | Article | zbapp | DM
380 | ETNT |  | Tues | 2016-01-06 | Wed | unhealthyveggies | Article | etntde | DM
381 | ETNT |  | Weds | 2016-01-07 | Thu | dryjanuary | Main Story | etntabs | DM
382 | ETNT |  | Thurs | 2016-01-08 | Fri | breadtrick | Article | eatthis.com | DM
383 | ETNT |  | Thurs | 2016-01-09 | Sat | tacobellrank | Article | zbcook | DM
384 | ETNT |  | Thurs | 2016-01-10 | Sun | sugarpanel | TBD |  | JP
385 | ETNT |  | Thurs | 2016-01-11 | Mon |  | ZBD Main Story |  | JP
386 | ETNT |  | Fri | 2016-01-11 | Mon | kindbarrank | Article | teaspot | DM
387 | ETNT |  | Mon | 2016-01-12 | Tue | traderjoes | Article | greentea | DM | green tea now in paperback
388 | ETNT |  | Fri | 2016-01-12 | Tue | greenteapaperonsale |  |  | JP
389 | ETNT |  | Tues | 2016-01-13 | Wed | cheapfoodsforabs | Main Story | zbapp | DM
390 | ETNT |  | Weds | 2016-01-14 | Thu | foodshungrier | Article | etntde | DM
391 | ETNT |  | Thurs | 2016-01-15 | Fri | suguariestmeals | Article | etntabs | DM
392 | ETNT |  | Thurs | 2016-01-16 | Sat | sodabellyvideo | Article | teacleanse | DM
393 | ETNT |  | Fri | 2016-01-17 | Sun | etntdefulllist |  |  | JP
394 | ETNT |  | Fri | 2016-01-18 | Mon | turkeyneck | Article | etntgame | DM
395 | ETNT |  | Fri | 2016-01-19 | Tue | worstbedtimefoods | Article | zbsmoothies | DM
396 | ZB | Y |  | 2016-01-19 | Tue |  | ZBD Main Story |  |  | Pick up 385
397 | ZB |  |  | 2016-01-19 | Tue | smoothiesonsale | Promo |  | JP
398 | ETNT |  |  | 2016-01-20 | Wed | metabolismbreakfast | Main Story | greentea | DM
399 | ETNT |  |  | 2016-01-21 | Thu |  | Article | zbapp
400 | ETNT |  |  | 2016-01-22 | Fri |  |  | zbcook
401 | ETNT |  |  | 2016-01-23 | Sat |  |  | etntabs
402 | ETNT |  |  | 2016-01-24 | Sun | hamptonslane |  |  | JP
403
404
405
406
407
408
409
410
411
412
413
414

## archive 109-245
Article-focused template: https://docs.google.com/a/galvanized.com/document/d/1QOjKruOSN_9ADKvfl7eKSEyVikarBIQLfEV5FMkK8Qk/edit
Main-story focused template: https://docs.google.com/a/galvanized.com/document/d/1fZy39nrUd_4qbecB1hbckphDuonQLNhmBXoH2A81J6s/edit
NOTES
No. | Brand | Releases | Day | Due | Content | Design | Promo | Who Starts It | Status/ Comments
108 | ETNT | 2015-05-02 | Sat/Sun | 2015-04-30 14:00 | lowcarb | Main story | etntmag | LZ
109 | ETNT | 2015-05-04 | Mon | 2015-05-01 12:00 | bestcheese | Article | zbd | LZ
112 | ETNT | 2015-05-06 | Weds | 2015-05-05 14:00 | notworth | Article | 2015book | LZ
113 | ETNT | 2015-05-07 | Thurs | 2015-05-05 14:00 | Bonus Edit (videos): |  | etntde | LZ
111 | ETNT | 2015-05-07 | Thurs |  | Global Winback 3: rulesfatloss |  | none | DC
114 | ETNT | 2015-05-08 | Fri | 2015-05-07 14:00 | oneday | Article | eatthis.com | LZ
110 | ETNT | 2015-05-08 | Fri |  | Winback 9: rulesfatloss |  | none | DC
115 | ETNT | 2015-05-09 | Sat/Sun | 2015-05-07 14:00 | cantricks | Main story | none | LZ
116 | ETNT | 2015-05-11 | Mon | 2015-05-08 12:00 | ruindiet | Article | none | LZ
117 | ETNT | 2015-05-15 |  |  | Winback 10: 11 processed (check for past usage) |  | none | DC
118 | ETNT | 2015-05-14 |  |  | Global Winback 4: 11 processed |  | etntmag | DC
119 | ETNT | 2015-05-14 | Thurs | 2015-05-12 14:00 | worsthealthy | Article | zbd | LZ
120 | ETNT |  | Weds |  | BookContinuityPromo-test | Promo |  | DC
121 | ETNT | 2015-05-13 | Weds | 2015-05-12 14:00 | Bonus Edit (restaurants):
122 | ETNT | 2015-05-15 | Fri | 2015-05-14 14:00 | icecream | Article | zbd | LZ
123 | ETNT | 2015-05-16 | Sat/Sun | 2015-05-14 14:00 | overpriced | Main story | 2015book | LZ
120 | ETNT |  | Sat/Sun |  | BookContinuityPromo-global | Promo |  | DC
124 | ETNT | 2015-05-18 | Mon | 2015-05-15 12:00 | badveggies | Article | none | LZ
125 | ETNT |  |  |  | Winback 11: |  |  | DC
126 | ETNT |  |  |  | Global Winback 5 (scrapped for 2015book promo) |  |  | DC
127 | ETNT | 2015-05-20 | Weds | 5/19 2:00PM | bestveggies | Article | etntde | LZ | Continuity Promo
128 | ETNT | 2015-05-21 | Thurs | 2015-05-20 14:00 | protein | Article | none | LZ
129 | ETNT | 2015-05-22 | Fri | 5/21 2:00PM | bestburger | Main Story | eatthis.com | LZ
130 | ETNT | 2015-05-23 | Sat/Sun | 5/21 2:00PM | drnotthat | Article | etntmag | LZ
131 | ETNT | 5/25/2015 | Mon | 5/22 12:00PM | needtoeat | Article | zbd | LZ
132 | ETNT |  |  |  | Active Winback TBD |  |  | DC
133 | ETNT |  |  |  | Global Winback TBD |  |  | DC
134 | ETNT | 5/27/2015 | Weds | 5/26 2:00PM | proteinshakes | Article | 2015book | LZ | Global winback Premium 1
135 | ETNT | 5/28/2015 | Thurs | 5/27 2:00PM | bestcarbs | Main Story | none | LZ
136 | ETNT | 5/29/2015 | Fri | 5/28 2:00PM | bestcandies | Article | etntde | LZ
137 | ETNT | 5/30/2015 | Sat/Sun | 5/28 2:00PM | superfoods | Article | eatthis.com | LZ
138 | ETNT | 6/1/2015 | Mon | 5/29 12:00PM | fathabits | Article | etntmag | LZ
139 | ETNT |  |  |  | Active Winback TBD |  |  | DC
140 | ETNT |  |  |  | Global Winback TBD |  |  | DC
141 | ETNT | 6/3/2015 | Weds | 6/2 2:00PM | destroydiet | Main Story | zbd | LZ | Global winback Premium 2
142 | ETNT | 6/4/2015 | Thurs | 6/3 2:00PM | perfectsalad | Article | 2015book | LZ | BEST LIFE POSSIBLE LAUNCH 1
143 | ETNT | 6/5/2015 | Fri | 6/4 2:00PM | flatstomach | Article | none | LZ
144 | ETNT | 6/6/2015 | Sat/Sun | 6/4 2:00PM | rapidwl | Article | etntde | LZ
145 | ETNT | 6/8/2015 | Mon | 6/5 12:00PM | forgood | Main Story | eatthis.com | LZ
146 | ETNT |  |  |  | Global winback3_v1 |  |  | DC
147 | ETNT |  |  |  | Global winback3_v2 |  |  | DC
148 | ETNT | 6/10/2015 | Weds | 6/9 2:00PM | teastory | Main Story | etntmag | LZ | Global winback all-out
149 | ETNT | 6/11/2015 | Thurs | 6/10 2:00PM | warninglabels | Article | zbd | LZ | BEST LIFE POSSIBLE LAUNCH 2
150 | ETNT | 6/12/2015 | Fri | 6/11 2:00PM | smoothieingredients | Article | none | LZ | Advertorial on eatthis.com takes over position 1
151 | ETNT | 6/13/2015 | Sat/Sun | 6/11 2:00PM | bestyog | Article | 2015book | LZ
152 | ETNT | 6/15/2015 | Mon | 6/12 12:00PM | badbelly | Main Story | etntde | LZ
153 | ETNT |  | Tuesday |  | Tea Cleanse Book release | Promo |  | DC
154 | ETNT |  |  |  | Global Winback TBD |  |  | DC
155 | ETNT | 6/17/2015 | Weds | 6/16 2:00PM | bwsnacks | Article | eatthis.com | LZ | Advertorial on eatthis.com takes over position 1
156 | ETNT | 6/18/2015 | Thurs | 6/17 2:00PM | proteinbars | Article | etntmag | LZ
157 | ETNT | 6/19/2015 | Fri | 6/18 2:00PM | restaurantreport | Article | zbd | LZ
158 | ETNT | 6/20/2015 | Sat/Sun | 6/18 2:00PM | healthychains | Main Story | 2015book | LZ
159 | ETNT | 6/22/2015 | Mon | 6/19 12:00PM | detoxhabits | Article | none | LZ
160 | ETNT |  |  |  | Active Winback TBD |  |  | DC
161 | ETNT |  |  |  | Global Winback TBD |  |  | DC
162 | ETNT | 6/24/2015 | Weds | 6/23 2:00PM | badbreakfast | Article | etntde | LZ
163 | ETNT | 6/25/2015 | Thurs | 6/24 2:00PM | beatbloat | Article | eatthis.com | LZ
164 | ETNT | 6/26/2015 | Fri | 6/25 2:00PM | trainernos | Main Story | etntmag | LZ
165 | ETNT | 6/27/2015 | Sat/Sun | 6/25 2:00PM | newfruits | Article | zbd | LZ | Advertorial on eatthis.com takes over position 1
166 | ETNT | 6/29/2015 | Mon | 6/26 12:00PM | worstburgers | Article | 2015book | LZ
167 | ETNT |  |  |  | Active Winback TBD |  |  | DC
168 | ETNT |  |  |  | ETNTMagPromo01 |  |  | DC
169 | ETNT | 7/1/2015 | Weds | 6/30 2:00PM | nogym | Article | none | LZ
170 | ETNT | 7/2/2015 | Thurs | 7/1 2:00PM | energybites | Main Story | etntde | LZ
171 | ETNT | 7/3/2015 | Fri | 7/2 2:00PM | worstyog | Article | eatthis.com | LZ
172 | ETNT | 7/4/2015 | Sat/Sun | 7/2 2:00PM | bestworst | Article | etntmag | LZ
173 | ETNT | 7/6/2015 | Mon | 7/3 12:00PM | fivemins | Article | zbd | LZ
174 | ETNT |  |  |  | Active Winback TBD |  |  | DC
175 | ETNT |  |  |  | Global Winback TBD |  |  | DC
176 | ETNT | 7/8/2015 | Weds | 7/7 2:00PM | blueberries | Main Story | 2015book | LZ
177 | ETNT | 7/9/2015 | Thurs | 7/8 2:00PM | newfastfood | Article | none | LZ
178 | ETNT | 7/10/2015 | Fri | 7/9 2:00PM | workoutfoods | Article | etntde | LZ
179 | ETNT | 7/11/2015 | Sat/Sun | 7/9 2:00PM | bestdiet | Article | eatthis.com | LZ
180 | ETNT | 7/13/2015 | Mon | 7/10 12:00PM | worstnuts | Main Story | etntmag | LZ
181 | ETNT |  |  |  | Active Winback TBD |  |  | DC
182 | ETNT |  |  |  | Global Winback TBD |  |  | DC
183 | ETNT | 7/15/2015 | Weds | 7/14 2:00PM | quitsoda | Article | zbd | LZ
184 | ETNT | 7/16/2015 | Thurs | 7/15 2:00PM | highprotein | Article | 2015book | LZ
185 | ETNT | 7/17/2015 | Fri | 7/16 2:00PM | nighttime | Article | none | LZ
186 | ETNT | 7/18/2015 | Sat/Sun | 7/16 2:00PM | summerbelly | Main Story | etntde | LZ
187 | ETNT | 7/20/2015 | Mon | 7/17 12:00PM | happyyog | Article | eatthis.com | LZ
188 | ETNT |  |  |  | Active Winback TBD |  |  | DC
189 | ETNT |  |  |  | Global Winback TBD |  |  | DC
190 | ETNT | 7/22/2015 | Weds | 7/21 2:00PM | complete | Article | etntmag | LZ
191 | ETNT | 7/23/2015 | Thurs | 7/22 2:00PM | bestworkout | Article | zbd | LZ
192 | ETNT | 7/24/2015 | Fri | 7/23 2:00PM | worstchoc | Main Story | zbapp | LZ
193 | ETNT | 7/25/2015 | Sat/Sun | 7/23 2:00PM | lemontea | Article | 2015book | LZ
194 | ETNT | 7/27/2015 | Mon | 7/24 12:00PM | skipgym | Article | Instagram | LZ
195 | ETNT | 2015-07-26 | Sun | 2015-07-24 14:00 | Unilever Takeover1 | Main Story | none | ?
196 | ETNT | 2015-07-28 | Tues | 7/2712:00PM | Unilever Takeover2 | Main Story | none | ?
197 | ETNT | 2015-07-29 | Weds | 7/28 4PM | exactcals | Article | none | LZ
198 | ETNT | 2015-07-30 | Thurs | 7/28 4PM | cutcarbs | Main Story | etntde | LZ
199 | ETNT | 2015-07-31 | Fri | 7/29 4PM | worstnutbutter | Article | eatthis.com | LZ
200 | ETNT | 2015-08-01 | Sat/Sun | 7/29 4PM | masonjar | Article | etntmag | LZ
201 | ETNT | 2015-08-03 | Mon | 7/31 12:00PM | proteinsnacks | Article | zbd | LZ
202 | ETNT | 2015-08-09 | Sun | 7/31 12:00PM | Unilever Takeover3 | Main Story | zbapp | ?
203 | ETNT |  |  |  | Global Winback TBD |  |  | DC
204 | ETNT | 2015-08-05 | Weds | 8/4 2:00PM | tonedbody | Main Story | 2015book | LZ
205 | ETNT | 2015-08-06 | Thurs | 8/5 2:00PM | onecoke | Article | none | LZ
206 | ETNT | 2015-08-07 | Fri | 8/6 2:00PM | fitnessfoods | Article | zbapp | LZ
207 | ETNT | 2015-08-08 | Sat/Sun | 8/6 2:00PM | mealprep | Article | eatthis.com | LZ
208 | ETNT | 2015-08-10 | Mon | 8/7 12:00PM | badsmoothie | Main Story | etntmag | LZ
209 | ETNT | [6 empty] | DC
210 | ETNT | [6 empty] | DC
211 | ETNT | 8/12/2015 | Weds | 8/11 2:00PM | omega3 | Article | etntde | LZ
212 | ETNT | 8/13/2015 | Thurs | 8/12 2:00PM | etntbreakfast | Article | zbd | LZ
213 | ETNT | 8/14/2015 | Fri | 8/13 2:00PM | perfectprotein | Article | 2015book | LZ
214 | ETNT | 8/15/2015 | Sat/Sun | 8/13 2:00PM | notlosing | Main Story | none | LZ
215 | ETNT | 8/17/2015 | Mon | 8/14 12:00PM | slimsecrets | Article | zbapp | LZ
216 | ETNT | 8/13-8/17 | Thurs/Fri tests, remainder Sunday | 8/12 4PM | unbox | Main Story | none | LZ/DC | TEST AND ALT MAILING - UNBOXED GIF
217 | ETNT | 8/18/2015 | Tues | 8/14 12PM | badhabits | Article | none | LZ
218 | ETNT | 8/19/2015 | Weds | 8/18 2:00PM | eatinghabits | Article | eatthis.com | LZ
219 | ETNT | 8/20/2015 | Thurs | 8/19 2:00PM | tilapia | Article | etntmag | LZ
220 | ETNT | 8/21/2015 | Fri | 8/20 2:00PM | fourteenways | Main Story | etntde | LZ
221 | ETNT | 8/22/2015 | Sat/Sun | 8/20 2:00PM | rapidwl | Article | zbd | LZ
222 | ETNT | 8/24/2015 | Mon | 8/21 12:00PM | lookbetternaked | Article | 2015book | LZ
223 | ETNT | 2015-08-25 | Tues | 8/24 2PM | worsthealthy | Article | none | DC
224 | ETNT | [6 empty] | DC
225 | ETNT | 8/26/2015 | Weds | 8/25 2:00PM | fiftypounds | Main Story | none | LZ
226 | ETNT | 8/27/2015 | Thurs | 8/26 2:00PM | supps | Article | zbapp | LZ
227 | ETNT | 8/28/2015 | Fri | 8/27 2:00PM | fitigers | Article | eatthis.com | LZ
228 | ETNT | 8/29/2015 | Sat/Sun | 8/27 2:00PM | worsticecream | Article | etntmag | LZ
229 | ETNT | 8/31/2015 | Mon | 8/28 12:00PM | lemonwater | Main Story | etntde | LZ
230 | ETNT | 9/1/2015 | Tues | 8/31 2:00PM | stupidsimple | Article | zbd | DC
231 | ETNT | [6 empty] | DC
232 | ETNT | 9/2/2015 | Weds | 9/1 2:00PM | bellyfat | Article | 2015book | LZ
233 | ETNT | 9/3/2015 | Thurs | 9/2 2:00PM | redmeat | Article | none | LZ
234 | ETNT | 9/4/2015 | Fri | 9/3 2:00PM | sexlife | Main Story | zbapp | LZ
235 | ETNT | 9/5/2015 | Sat/Sun | 9/3 2:00PM | thyroid | Article | eatthis.com | LZ
236 | ETNT | 9/7/2015 | Mon | 9/4 12:00PM | mindfuleating | Article | etntmag | LZ
237 | ETNT | 9/8/2015 | Tues | 9/7 2:00PM | workouthabits | Article | etntde | DC
238 | ETNT | [6 empty] | DC
239 | ETNT | 9/9/2015 | Weds | 9/8 2:00PM | worstoats | Main Story | zbd | LZ
240 | ETNT | 9/10/2015 | Thurs | 9/9 2:00PM | bestchoc | Article | 2015book | LZ
241 | ETNT | 9/11/2015 | Fri | 9/10 2:00PM | fruitbloat | Article | none | LZ
242 | ETNT | 9/12/2015 | Sat/Sun | 9/10 2:00PM | nocoke | Article | zbapp | LZ
243 | ETNT | 9/14/2015 | Mon | 9/11 12:00PM | greentea | Main Story | teacleanse | LZ
244 | ETNT | 9/15/2015 | Tues | 9/14 2:00PM | anxietyfood | Article | zbcook | DC
245 | ETNT | 2015-09-20 | Sun |  | de4preview | DEPreview |  | DC
PLEASE SEE NEW SHEET

## archive-60-109
Article-focused template: https://docs.google.com/a/galvanized.com/document/d/1QOjKruOSN_9ADKvfl7eKSEyVikarBIQLfEV5FMkK8Qk/edit
Main-story focused template: https://docs.google.com/a/galvanized.com/document/d/1fZy39nrUd_4qbecB1hbckphDuonQLNhmBXoH2A81J6s/edit
No. | Brand | Releases | Day | Due | Content | Design | Promo | Who Starts It | Status/ Comments | Notes: —Use the word "source" to indicate that it should pull from title, description or image already online. —Otherwise, type it explicitly, and for image put an actual image file name (and put the image on the server in sourceImages(live) folder —Use the promo code following the key in the templates —In general please use Google's "insert comment" to leave me notes - better than typing into fields which tie into automation —Please use <em></em> for itals Thank you! :)
60 | ETNT |  |  |  | Rapid Weight Loss | Article
61 | ETNT |  |  |  | End Overeating | Main story
62a | ETNT |  |  |  | Meet the new ETNT | Letter |  |  | "Meet the new ETNT" - winback - LZ version (heartfelt) 2 stories below
62b | ETNT |  |  |  | Meet the new ETNT | Letter |  |  | "Meet the new ETNT" - winback - SP version (promotional) 2 stories below
63 | ETNT |  |  |  | Abs | Main story |  |  | Share and recieve a free gift is the main push Article focused, including hilight videos
64 | ETNT |  |  |  | 2015 Book (Daniel C produces) | Promo
65 | ETNT |  |  |  | trainerpicks | Article
66 | ETNT |  |  |  | foodpairings | Main story
67 | ETNT | 2015-03-13 |  |  | cleansnacks | Article
69 | ETNT | 2015-03-16 | Sat/Sun |  | mariamenounos | Article | eatthis.com
70 | ETNT | 2015-03-15 | Sun |  | 2inback 2: bestjunkfood | Main story | none
68 | ETNT | 2015-03-16 | Mon |  | bestfuelworkout | Main story | eatthis.com | LZ
71 | ETNT | 2015-03-18 | Weds | 2015-03-17 16:00 | healthyvices | Main story | zbd | LZ
72 | ETNT | 2015-03-19 | Thurs | 2015-03-18 16:00 | 2015 book promo | TBD | TBD | DC/JP
73 | ETNT | 2015-03-20 | Fri | 2015-03-18 16:00 | lookbetternaked | Article | 2015book | LZ
74 | ETNT | 2015-03-21 | Sat/Sun | 2015-03-19 14:00 | unhealthiestfoods | Article | eatthis.com | LZ
75 | ETNT | 2015-03-23 | Mon | 2015-03-20 12:00 | abspop | Main story | zbd | LZ
76 | ETNT | 2015-03-24 | Tues | 2015-03-23 12:00 | Winback 3: unhealthiestfoods- | Article | none | DC
77 | ETNT | 2015-03-25 | Weds | 2015-03-24 14:00 | cleanjunkfood | Article | none | LZ
78 | ETNT | 2015-03-27 | Fri | 2015-03-25 14:00 | bellyfatfoods | Main story | 2015book | LZ
79 | ETNT | 2015-03-28 | Sat/Sun | 2015-03-26 14:00 | tendayplan | Article | eatthis.com | LZ
80 | ETNT | 2015-03-30 | Mon | 2015-03-27 12:00 | cookingtips | Article | etntmag | LZ
81 | ETNT | 2015-03-31 | Tues | 2015-03-30 | Winback 4: cleanjunkfood |  | zbd | DC
82 | ETNT | 2015-04-01 | Weds | 2015-03-31 14:00 | loseweightin10 | Main story | none | LZ
83 | ETNT | 2015-04-03 | Fri | 2015-04-01 14:00 | gainingweight | Article | 2015book | LZ
84 | ETNT | 2015-04-04 | Sat/Sun | 2015-04-02 14:00 | celebritytrainer | Main story | eatthis.com | LZ
85 | ETNT | 2015-04-06 | Mon | 2015-04-03 12:00 | addictivefoods | Main story | etntmag | LZ
86 | ETNT | 2015-04-08 | Weds | 2015-04-06 | Winback 5: healthyvices | Main story | none | DC
87 | ETNT | 2015-04-08 | Weds | 2015-04-07 14:00 | processedfoods | Article | zbd | LZ
88 | ETNT | 2015-04-10 | Fri | 2015-04-08 14:00 | bestmilk | Article | 2015book | LZ
89 | ETNT | 2015-04-11 | Sat/Sun | 2015-04-09 14:00 | worstchicken | Main story | eatthis.com | LZ
90 | ETNT | 2015-04-13 | Mon | 2015-04-10 12:00 | cheapsupermarkets | Article | etntmag | LZ
91 | ETNT | 2015-04-14 | Tues | 4/13/2015 | Winback 6: processedfoods |  | none | DC
92 | ETNT | 2015-04-15 | Weds | 2015-04-14 14:00 | losefatfaster | Article | zbd | LZ
93 |  | 4/16/2015- 4/19/2015 |  |  | Global Winback 1: unhealthiestfoods, and eatthiscom
94 | ETNT | 2015-04-17 | Fri | 2015-04-15 14:00 | besteversnacks | Main story | none | LZ
95 | ETNT | 2015-04-18 | Sat/Sun | 2015-04-16 14:00 | bestcereal | Article | 2015book | LZ
96 | ETNT | 4/20/2015 | Mon | 2015-04-17 12:00 | etntabs | Article | eatthis.com | LZ
97 | ETNT | 4/21/2015 | Tues | 4/20/2015 | Winback 7: cleanjunkfoods (might be 104) |  | none | DC
98 | ETNT | 4/22/2015 | Weds | 2015-04-21 14:00 | rulesfatloss | Main story | etntmag | LZ
99 | ETNT | 2015-04-23 | Thurs | 2015-04-22 14:00 | Bonus Edit: bonus1weightloss | Article | none | LZ
100 | ETNT | 4/24/2015 | Fri | 2015-04-22 14:00 | fitnessmistakes | Article | zbd | LZ
101 | ETNT | 4/25/2015 | Sat | 2015-04-23 14:00 | flatbellykitchen | Article | none | LZ
102 | ETNT | 4/27/2015 | Mon | 2015-04-24 12:00 | healthygut | Article | 2015book | LZ
103 | ETNT | 2015-04-27 | Mon | 2015-04-24 12:00 | Global Winback 2: cleanjunkfoods | Article | none | DC
104 | ETNT | 4/28/2015 | Tues | 2015-04-27 14:00 | Winback 8: bestcereal (might be 97) |  |  | DC
105 | ETNT | 4/29/2015 | Weds | 2015-04-28 14:00 | expertlunch | Main story | etntde | LZ | for etntde promo, it's okay to pull new images each time
106 | ETNT | 2015-04-30 | Thurs | 2015-04-28 14:00 | Bonus Edit: bonus2recipes | Article | eatthis.com | LZ
107 | ETNT | 5/1/2015 | Fri | 2015-04-29 14:00 | leanmuscle | Article | none | LZ
108 | ETNT | 5/2/2015 | Sat/Sun | 2015-04-30 14:00 | lowcarb | Main story | etntmag | LZ
109 | ETNT | 5/4/2015 | Mon | 2015-05-01 12:00 | bestcheese | Article | zbd | LZ
#REF! | ETNT | 2015-05-06 | Weds | 5/5 2:00PM | notworth | Article | 2015book | LZ
#REF! | ETNT | 2015-05-07 | Thurs | 5/5 2:00PM | Bonus Edit (videos): |  | etntde | LZ | for etntde promo, it's okay to pull new images each time
#REF! | ETNT | 2015-05-07 | Thurs | #REF! | Global Winback 3: rulesfatloss |  | none | DC
PLEASE SEE NEW SHEET